## 表紙 (hidden)
第１．０版
2019-07-31
関係者外秘
PJ関係者限り
Nablarch
Nablarchを使用した開発の流れ

## 変更履歴 (hidden)
PJ名 | [5 empty] | 成果物名 |  | Nablarchを使用した開発の流れ | 作成 | TIS |  | 2019-07-31
システム名 | [8 empty] | 変更
サブシステム名
変更履歴（ 1 / 1 ）
No. | 版数 | 変更日 | 区分 | 変更箇所（項番等） |  |  | 変更内容 |  |  |  | 担当者
1 | 1.0版 | 2019-07-31 | 新規 | - |  |  | (新規作成) |  |  |  | TIS

## Flow of Nablarch Development
Flow of Development Using Nablarch
Environment construction
| □ Repository environment | □ Design environment | □ CI environment | □ Local development environment (including unit test execution environment) | □ Integration test environment
| □ Mock-up creation environment |  |  |  |  | - DB construction, data input
- AP server construction, application deployment
Dummy
UI standard
Application engineer
Architect
Requirement definition
Design
Programming Unit testing
Domain definition
design document
ER diagram
(Logical model)
DB schema
common test
data
Screen design
Screen switching diagrams
<<Action>>
Business action
Base component
design document
Base component
implementation
Base component
list
Base component
design
ER diagram
(conceptual model)
Common component
design
Project
term dictionary
Code design document
<<use>>
<<Entity>>
Evidence
Tested code
build and deploy
Creating common test data
Common test data
AP server
(integration test environment, etc.)
Combined test
Source code
- Static analysis tool
- various check tools
EDM
Check
Correction
Business flow diagram
Functions list
DB design (physical)
Cannot be modified
No unit test required
<<Service>>
Services
<<Component>>
Base components
DB design (physical)
ER diagram
(physical model)
DB development support tool
Data modeler
Domain
Bean
Data analyst
Overall
system diagram
Function requirements document
Subfunction unit test
Key test of the subfunction unit on the application server in the local environment
Class unit test
Automatic test for business form and business logic components
Class unit test
preparation
<<Test>>
Test code
Class unit test
implementation
Subfunction unit test implementation
Subfunction test specification document
Unit test standards
<<Form>>
Business form
System design document
Screen mockup
(Design HTML)
<<JSP>>
business screen JSP
<<use>>
Table definition document
Data pattern table
Coding conventions
Site map
Wire frame
Non-functional requirements document
Identification of
data patterns
External interface
design
External interface
list
External interface
design
Unit test results
evidence
Table list
Requirement definer/designer
Common component list
System function
design document (screen)
Message design document
SQL verification
(Feasibility/Performance confirmation)
App implementation
Feedback from
design
Unit test case
design
Unit test specification document
Unit test specification
(Format)
Unit test standards
Coding conventions
Deliverables created individually in the project
Deliverables that reflect PJ requirements for the terms and guides provided as
Nablarch development standards
Legend
Task to be performed
Deliverables such as source code and test data
Running the tool
Input and output during task execution
Input and output during tool execution
Context between deliverables
Created deliverables
Created deliverables (terms and guides reflecting PJ requirements)
Request list
Numbering list
<<Component>>
Base components
EDM
Batch design
Screen switching diagrams
Net job
flow
Job flow design
Formulation of development standard
Data definition
Reference of
method and standard
Reference of
data model
Reference of
data model
Feedback from
design
<<SQL>>
SQL file
Deliverables that reflect PJ requirements in the format provided as
Nablarch development standards
System
process flow
System
functions list
Screen list
Development guide
Common component design document
<<Component>>
Shared components
<<SQL>>
SQL file
Sample
application
Sample implementation
(Advanced development)
Development guide
ID system
Code class
Test data
Data output tool for code table registration
Test data
System function
design document (Web service)
Web service design
System function
design document(batch)
Request list
Web service API
list