## Cover
Version 1.2
2022-08-04
[Company name]
[Department name]
CONFIDENTIAL
PROJECT PERSONNEL ONLY
Sample Project
Unit Test Standard

## Revision history
Project name |  |  | Sample Project |  |  |  | Deliverable name |  | Unit Test Standard | Prepared by | TIS |  | 2018-08-24
System name |  |  | Sample System | [6 empty] | Changes | TIS |  | 2022-08-04
Sub-system name
Revision history（ 1 / 1 ）
No. | Version No. | Revision date |  | classification | Changes(item numbers, etc.) |  |  | Revision details |  |  |  | Person in charge
1 | Version 1.0 | 2018-08-24 |  | New | - |  |  | (New creation) |  |  |  | TIS
2 | Version 1.1 | 2020-01-20 |  | Modfy | 3.3.3. trading unit test evidence |  |  | Added the following as evidence for a screen transaction unit test. ・test plan ・Response HTML |  |  |  | TIS
3 | Version 1.2 | 2022-08-04 |  | Modfy | 3.1 Overview of Unit Testing |  |  | Modify the correspondence table between the test viewpoint catalog and the test specification format. |  |  |  | TIS

## Contents
Project name |  |  | Sample Project | Deliverable name |  | Unit Test Standard | Prepared by | TIS | 2018-08-24
System name |  |  | Sample System |  |  |  | Changes | TIS | 2022-08-04
Sub-system name
Contents
1. About this document
1.1. Particulars and purpose of this document
1.2. Reference Documents
2. Unit test policies
2.1. Basic Policy
2.2. Unit test system
2.3. Unit test environment
2.4. Unit test completion conditions
3. Overview of unit test
3.1. Unit of creation of unit testing specifications
3.2. Overview of viewpoint of unit test
3.3. Evidence of unit test

## 1
Project name |  |  |  | Sample Project | Deliverable name | Unit Test Standard | Prepared by | TIS | 2018-08-24
System name |  |  |  | Sample System |  |  | Changes | TIS | 2022-08-04
Sub-system name
1. About this document
1.1. Particulars and purpose of this document
The purpose of this document is to explain the test policies and perspectives for unit test to prevent variance in quality between application programmers.
This document describes the policies, scope and perspectives of unit test in this project.
Please note that this document covers the minimum necessary perspectives to be considered when conducting unit test.
Some functions may require confirmation from additional perspectives during test.
1.2. Reference Documents
This document relies on the following documents to develop test policies and viewpoint.
・Testing viewpoint catalog
・Testing type catalog
Both are available at the following URL. Refer to as necessary.
https://fintan.jp/page/1456/
The unit test specification format is available in the same folder as this document.

## 2
Project name |  |  |  | Sample Project |  |  |  | Deliverable name |  | Unit Test Standard |  |  | Prepared by | TIS | 2018-08-24
System name |  |  |  | Sample System | [8 empty] | Changes | TIS | 2022-08-04
Sub-system name
2. Unit test policies
|  | 2.1. | Basic Policy
In the past, unit test for Nablarch development was mostly automated using the Nablarch Testing Framework (NTF).
However, while this method can obtain high coverage, it requires a large cost to create and maintain test data.
Therefore, this project adopts a method that emphasizes the balance between cost and quality.
Specifically, automated test by NTF will be limited to REST and batch, and will not be used in the screen processing architectures.
Instead, the part of the screen processing architecture that has been confirmed by the automatic test of NTF in the past will be confirmed manually in the subfunction unit tests.
Tests for simple validation of Forms should not be automated by NTF regardless of the processing architectures.
In Nablarch, simple validation of a Form can be achieved by setting annotations.
Therefore, it is sufficient to ensure the quality of the validation only by checking whether the design document and the annotation settings match.
For this reason, simple validation of Forms can be done only by theoretical verification instead of automated test to reduce costs.
|  | 2.2. | Unit test system
In this project, unit tests are divided into class unit tests, request unit tests, and subfunction unit tests.
Below is a list of the unit tests to be conducted by application programmers.
|  |  | Test |  |  | Description
|  |  | Class Unit Test |  |  | Tests conducted for each class. These tests are used to check that each class operates correctly as a unit. Tests are conducted based on stereotypes of each form class, entity class, action class and common component class. This corresponds to the "module unit" in the testing type catalog.
|  |  | Request Unit Test |  |  | Tests conducted for each request. After ensuring the quality of forms, entities, actions and some common components in class unit testing, the classes are combined and request unit testing is conducted to confirm that operations are performed correctly when each processing request is received. This corresponds to "Screen and batch units" in the testing type catalog.
|  |  | Subfunction Unit Test |  |  | Tests conducted for each business subfunction*1. After ensuring the quality of each request during request unit testing, the requests are combined as business subfunctions and subfunction unit testing is conducted to confirm that operations are performed correctly when each business subfunction operates. This corresponds to the "use case unit" in the testing type catalog.
|  |  | *1 | The minimum unit comprising a series of requests for business purposes.
Below is a summary of the test methods for each type of input process method.
Refer to the input process architecture in the system function list and the corresponding information in the table below to confirm the test method.
|  |  | Input process architecture Test type |  | Screen |  | Combination of screen and delayed*1 |  | on-demand batch |  | resident batch (delayed) | REST
|  |  | Class Unit Test |  | Automatic test |  | Automatic test |  | Automatic test |  | Automatic test | Automatic test
|  |  | Request Unit Test |  | Manual test/ Automatic test *2,*3 |  | Manual test / Automatic test *2,*3 |  | Automatic test |  | Automatic test | Automatic test
|  |  | Subfunction Unit Test |  | Manual test / Automatic test *3 |  | Manual test / Automatic test *3 |  | Automatic test |  | Automatic test | - *4
|  |  | *1 | Test that connects delayed screen processes and delayed processes that are launched (resident batch processes) is conducted in integration test.
|  |  | *2 | Screen request unit tests are performed in manual tests within subfunction unit tests.
|  |  | *3 | The first time is done by manual and the second and subsequent times are done using an automated subfunction unit test tool.
|  |  | *4 | Since a REST subfunction is completed with a single request, only request unit test is performed.
2.3. Unit test environment
Unit test is conducted in the development environment built on the developers' local computers.
2.4. Unit test completion conditions
Below are the completion conditions for unit test.
|  |  | ・ | All check results of checklist completion conditions for programming and unit test work must pass.
|  |  | ・ | All unit test cases must have been tested, and must all have passed test.
|  |  | ・ | All issues raised in the review of the unit test results must be resolved,
and a passing result must be achieved when test again for confirmation.
Scope of unit tests (scope of this document)
range after
integration test
Class Unit Test
Checking individual logic
Subfunction Unit Test
Business Subfunction unit testing
Cooperation between
subfunction, etc.
Except for unit tests, the range
to be performed up to integration test
Quality assurance by CheckStyle and
SpotBugs
Quality assurance through self-check
self-checking Source Code Review
(Theoretical)
etc.
Request Unit Test
Testing with classes in a combined

## 3.1
Project name |  |  |  | Sample Project |  | Deliverable name | Unit Test Standard | Prepared by | TIS | 2018-08-24
System name |  |  |  | Sample System |  |  |  | Changes | TIS | 2022-08-04
Sub-system name
3. Overview of unit test
|  | 3.1. | Unit of creation of unit testing specifications
Create one set of unit testing specifications for each set of system function design specifications or common component design specifications.
Unit testing specifications should indicate the class unit, request unit and subfunction unit test cases in the subfunction.
(This is because it is difficult to confirm whether the test cases are sufficient overall if unit testing specifications are created for each request unit test.)
|  | 3.2. | Overview of viewpoint of unit test
The unit test specification format for this project is based on the testing viewpoint catalog and unit test standards.
Add business test viewpoints to this and create test specifications.
The test specification format provides the following sheets for each test type.
・Class unit test
・Request unit test
・Subfunction unit test
Of these, class unit tests and request unit tests are created based on the test viewpoints listed in the testing viewpoint catalog.
In addition, the format of the subfunction unit test sheet has been created based on the viewpoints independently examined.
Below is the correspondence between the class unit test and request unit test sheets and the referenced testing viewpoint catalog sheet.
|  |  | Processing architectures |  | Sheet | Original testing viewpoint catalog sheet
|  |  | SCREEN |  | Class unit test | Function Test [Common]
[5 empty] | Request unit test | Function Test [Common], Functional Test [Web Application]
|  |  | REST |  | Class unit test | Function Test [Common]
[5 empty] | Request unit test | Function Test [Common], Functional Test [Web Service]
|  |  | BATCH |  | Class unit test | Function Test [Common]
[5 empty] | Request unit test | Function Test [Common], Functional Test [Batch Application]
All viewpoints listed in the testing viewpoint catalog were transcribed into the test specification format.
However, for items that can be judged to be unnecessary depending on the processing architectures and test type, items are grayed out in advance.
For items that have already been grayed out, the reasons for determining that they are unnecessary are listed in the "Reasons for exclusion" column.
If there is something that can be judged that the test is unnecessary individually from the viewpoint of business test, the items should be grayed out and the reason for the decision
to be unnecessary should be stated in the "Test Contents" column (so that it can be distinguished from those that have been grayed out in advance).
In addition, as stated in 2.1. Basic Policy, the appropriateness of annotations set on Forms and domain classes will be confirmed only on paper.
Therefore, the request unit test sheet does not include test cases covering validation patterns.
Instead, test cases should be developed to ensure that validation is working.
Business test viewpoint
System function
design specifications
Component design specifications
Unit test specification
Format
Testing viewpoint catalog
Unit test standard
(This document)
Unit test specification
Test designer
General test viewpoint

## 3.3
Project name |  |  | Sample Project | [6 empty] | Deliverable name |  |  | Unit Test Standard | Prepared by | TIS | 2018-08-24
System name |  |  | Sample System | [10 empty] | Changes | TIS | 2022-08-04
Sub-system name
3.3 Evidence of unit test
This section explains the evidence that needs to be obtained from unit test.
Evidence acquired from unit test must indicate the test details and test results.
3.3.1. Evidence of class unit tests
Evidence for a class unit test is not required.
3.3.2. Evidence of request unit tests
Evidence for a request unit test is not required.
3.3.3. Evidence of subfunction unit tests
(1) Screen/Combination of screen and delayed (Perspective on display control)
|  |  | Evidence |  |  |  | Required | Description
|  |  | Unit test specifications |  |  |  | X | A document indicating the test cases. The test results must be written.
|  |  | Hard copies of screens |  |  |  | X | Screenshots of the tested screens. Save these to digital media. Add comments as appropriate to show what you are checking. Get a hard copy at the display size defined in the UI standard. *However, if you want to include the developer tool window in the evidence, such as when you want to check the attributes of UI components or step through JavaScript, you may change the display size only for tests other than from the viewpoint of checking the layout.
|  |  | Test plan(jmx file) |  |  |  | X | Save the operations performed in the test on electronic media so that they can be rerun.
|  |  | Response |  |  |  | X | Store to simplify verification of results when the test is rerun.
(2) Screen/Combination of screen and delayed (perspectives on Combinations within subfunctions)
|  |  | Evidence |  |  |  | Required | Description
|  |  | Unit test specifications |  |  |  | X | A document indicating the test cases. The test results must be written.
|  |  | Hard copies of screens |  |  |  | X | Screenshots of the tested screens. Save these to digital media. Add comments as appropriate to show what you are checking. Get a hard copy at the display size defined in the UI standard. *However, if you want to include the developer tool window in the evidence, such as when you want to check the attributes of UI components or step through JavaScript, you may change the display size.
|  |  | test plan(jmx file) |  |  |  | X | Save the operations performed in the test on electronic media so that they can be rerun.
|  |  | response |  |  |  | X | Store to simplify verification of results when the test is rerun.
|  |  | Logs |  |  |  | X | Take two logs: a web server log and an application log. Check that no unexpected (fatal or error level) log items are output. Extract the log items for the tested subfunctions only.
|  |  | Database dumps |  |  |  | X | Acquire this for all data in all tables accessed during the tested processes.
For processes in which the database is updated, acquire a database dump before and after the update and details on the difference as evidence.
For tables that are updated or referenced by common components or framework utilities,
acquire data dumps for the table indicated in the applicable system function design specifications.
Example 1: If a common component is called to reference or update a database
(if information such as the following is written in the system function design specifications),
acquire a database dump for the corresponding table.
Example of information in design specifications
Update user management table.
⇒Component used: CM114001: Update user management table: Update primary key of user management table
Example 2: A dump does not need to be acquired for a table if the call side does not need to
recognize which table is called or referenced by the common component that is called.
Example of information in design specifications
Apply changes in user information to sales management system.
⇒Component used: CM021011: User management SS linking: Apply changes in user information
|  |  | Input data |  |  |  |  | Data (other than that in database) used as input for tested process. Does not need to be acquired if no data is used for input.
|  |  | Content output by process |  |  |  |  | Content output by tested subfunction (files, emails, ledgers, etc.)
(2) Other than, Screen/Combination of screen and delayed
|  |  | Evidence |  |  |  | Required | Description
|  |  | Unit test specifications |  |  |  | X | A document indicating the test cases. The test results must be written.
3.3.4. How to store evidence
Use the following folder tree to store evidence.
(This is only required for screen/combination of screen and delayed. Evidence does not need to be stored for other input process architectures,
as all unit test is conducted automatically for these.)
Evidence does not be stored for tests conducted using the unit test specifications or automatic test (this is managed in the repository).
[[Automated subfunction unit test execution tool]/src/test/resources]
└──[subfunction ID]
[5 empty] | └──[scenario ID] | [6 empty] | … | Create a folder for each scenario ID and store the evidence.
[6 empty] | ├──db_dump |  | (DB dump)
[6 empty] | ├──scenario |  | (test plan) |  |  |  |  | If there is more than one type of evidence under the scenario ID folder,
[6 empty] | ├──response |  | (response) |  |  |  |  | store a folder for each type of evidence.
[6 empty] | ├──input |  | (input data)
[6 empty] | ├──output |  | (output data) |  |  |  |  | Create a folder with the same name as shown in the left figure,
[6 empty] | ├──log |  | (log) |  |  |  |  | as it will be referenced by automated subfunction unit test execution tool
[6 empty] | └──hard_copy |  | (screen hard copy) |  |  |  |  | (see the tool's README for details).