## 表紙 (hidden)
第1.0版
2019年3月26日
この 作品 は | クリエイティブ・コモンズ 表示 - 継承 4.0 国際 ライセンス |  | の下に提供されています。
PG・UT作業の完了条件チェックリスト©2018 TIS INC. クリエイティブ・コモンズ・ライセンス（表示-継承 4.0 国際）
PG・UT作業の完了条件チェックリスト

## Case study
Example of implementation
Here is an example of a development process using the checklist of completion conditions for PG and UT work or checklist for self-assessment of results by programmers.
◎Prerequisites
・ | As the development for this project was contracted offshore, the checklist for self-assessment of results by programmers was used as a condition for completion of the contracted work.
・ | Some members of the team did not have experience with Nablarch and/or did not have strong skills with Java, so a review was conducted after these team members completed 30% of their work.
・ | After coding was completed, a comprehensive check was conducted by blacking out the specifications to confirm that the code had been written according to the design specifications with no omissions or errors.
Work process |  | Nature and viewpoint of work | By
|  | The programmers assess the functions and subfunctions. | Programmers
|  | Must be a case that complies with unit testing standards. Test cases covering the details in the design specifications must be created. | Programmers
|  | Code is written and unit testing is conducted for several requests according to the specifications that have been The programmers and technical supervisor must discuss the point at which a 30% review needs to be requested. The 30% PG/UT can be omitted in some cases, depending on the difficulty of each subfunction and the skill level of the programmer(s). | Programmers
|  | The coding and unit test results are checked using the following checklist. ・Checklist for self-assessment of results by programmers | Programmers
|  | The source code and tests are reviewed when 30% of the project has been completed. Conducting this review before all of the work has been completed enables issues to be detected early so that large amounts of backtracking will not be needed later. For example, if the project consists of five requests (initial viewing, list searching, registration, confirmation and completion), the review may be done after initial viewing and list searching have been completed. | Technical supervisor
|  | The remainder of coding and unit testing is conducted. | Programmers
|  | The coding and unit test results are checked using the following checklist. ・Checklist for self-assessment of results by programmers | Programmers
|  | A check is performed by blacking out the test specifications before the source code review. The purpose of this check is to confirm that the points in the design specifications (including screen layout) have been covered with no omissions or errors. | Programmers
|  | ■Technical review The results are reviewed from the following technical perspectives. ・Compliance with standards (Java Coding Standards, user interface standards, test standards) ・Common coding mistakes (BigDecimal, NullPoint, attachment files) ・Feasibility of standardization ・Readability of source code ・How to use the application framework function ・Application performance and security considerations ・Superfluous or missing tests ■Operational review The source code is cross-checked against the design specifications to confirm that it has been written according to the design specifications. This can be done by another team member if the reviewer does not have time (the main point of a cross-check is for the code to be checked by a third party.) | Technical supervisor
|  | The application is deployed on the application server and screen operations are tested. ・Display control, input control, JavaScript and the screen transitions within the project are confirmed. | Programmers
|  | The coding and unit test results are checked using the following checklist. ・Checklist of completion conditions for PG and UT work | Programmers
Writing of design specifications
Coding (30%)
Class unit testing
Request unit testing
Project unit test
Completion condition check
Source code and test review
(All)
Black out design specifications
Creation of unit test specifications
Source code and test review (30% mark)
Coding (All)
Class unit testing
Request unit testing
PG/UT (30%)
Check using checklist
Check using checklist
PG/UT (All)

## Checklist for PG and UT work
Checklist of completion conditions for PG and UT work
Project ID:
Project name:
1. Visual checks
|  | No | Check items | Details of check | Check method | Evaluation index | Required value | To be checked by | Check date | Check result | Comment
|  | 1 | Coding and unit testing | None of the coding errors that tend to occur during development must be present. | Perform a check using the checklist for self-assessment of results by programmers. | Number of defects | 0 defects
|  | 2 | Omissions in code | All of the points in the external and internal design specifications must be covered by the code, with no omissions. | Confirm this by blacking out the points in the external and internal design specifications that are covered by the source code. | Areas that are not blacked out | 0 remain- ing areas
2. Checks using tools
|  | No | Check items | Details of check | Check method | Evaluation index | Required value | To be checked by | Check date | Check result | Comment
|  | 1 | TODO comments | No TODO comments must be left in the source code or settings file. | Check that no TODO comments are left in the source code or settings file. ・Java ・jsp, sql, xml, config, properties, js | Number of remaining TODO comments | 0 com- ments
|  | 2 | Java source code | The code must not violate the method for writing Java source code that is generally recommended. | Perform a check using the static analysis tool or IDE (integrated development environment) function. | Number of errors or warnings | 0 errors or warnings
|  | 3 | Java compiling | It must be possible to compile the Java source code. | Perform a check using the JDK compiling function or IDE function. | Number of errors or warnings | 0 errors or warnings
|  | 4 | @Ignore annotations （@Ignore is an annotation used to indicate JUnits to be ignored during unit testing.) | No @Ignore annotations must be used. | Check that no tests with @Ignore appended are left. | Areas with @Ignore | 0 areas with @Ignore
|  | 5 | Automatic unit testing | All test code must pass automatic unit testing. | Check this by executing the test code using the IDE function. | Areas of code that fail the testing | 0 fail- ing areas
|  | 6 | Automatic unit testing coverage | All test code must be covered in the test target source code. | Check this by measuring test coverage with the IDE function. | Test coverage (C0 and C1) | 100%*１
*１ This excludes areas that are difficult to test automatically, such as code with the try-with-resources statement or processes where an SQLException occurs.
3. Checks to handle issues raised in review
|  | No | Check items | Details of check | Check method | Evaluation index | Required value | To be checked by | Check date | Check result | Comment
|  | 1 | Review completion rate | All of the results requiring a review must be reviewed. | Check the review status of the results requiring a review. | Completion rate | 100%
|  | 2 | Issues raised in source code review | All issues raised in the review must have been addressed. | Check whether the issues raised in the review have been addressed. | Remaining issues | 0 remain- ing issues
|  | 3 | Issues raised in review of unit test specifications and results | All issues raised in the review must have been addressed. | Check whether the issues raised in the review have been addressed. | Remaining issues | 0 remain- ing issues
4. Other checks
|  | No | Check items | Details of check | Check method | Evaluation index | Required value | To be checked by | Check date | Check result | Comment
|  | 1 | Remaining development items (missing items) | There must be no remaining development items (missing points). | Confirm whether there are any missing points based on the results of sections 1 to 3 above. If there are any missing items, the team handling the next phase(s) must be informed. The following details need to be confirmed for each missing point. (1) The nature of the missing point (2) Restrictions caused by the missing point (3) The date on which the missing point is expected to be addressed | Missing points | 0 missing points